## TestPlan
Output candidate recommendations ordered according to relevance.	Recommendation Engine Test Planner and Tracker
	Engine in Test implies that the Tester can give an input of the jobs/candidate for which he wants an candidates list/job recommendation and get and output.
	The tester also has admin access implying that he has access to the databases and can add/remove/view candidates profiles and job description.

Test Planner and Tracker				Himakar,Hemanth,Kriti,Suhan,Sarat
Test / No. ID	Related / Use case	Pre-conditions	Test Description (steps)	Expected Outcome	R1 Outcome (color code / cell background)	R2 Outcome (color code / cell background)	Comments (if test case failed)
1	Admin Login	Admin not logged in.	Logs in admin via login portal	Admin is logged in and can access ourfood site.	Unit Testing and Integration Testing will be done for R2.	User logs in as admin.
2	Admin Registration		Adds user account.	User is registered as admin	Unit Testing and Integration Testing will be done for R2.	User is registered
3	CRUD of farmer(Seller Account)	Seller logged in	CRUD seller account.	Selected accounts must be modified as per requirements depending on permissions of user.	Unit Testing and Integration Testing will be done for R2.	Properties of seller account changes as required
4	Farmer Registration		Adds farmer(seller) account.	User is registered as a seller	Unit Testing and Integration Testing will be done for R2.	User gets registered as seller.
5	Farmer Login	Farmer(seller) not logged in	Logs in farmer via login portal	Farmer is logged in and can access ourfood site	Unit Testing and Integration Testing will be done for R2.	User logs in as farmer.
6	Direct CRUD Produce(Farmer's order)	Seller logged in	CRUD produce items	Selected produce must be modified as per requirements depending on permissions of user.	Unit Testing and Integration Testing will be done for R2.	Properties of produce changes as required
7	Direct CRUD Product(Seller item of ourfood)	Admin logged in.	CRUD product items	Selected products must be modified as per requirements depending on permissions of user.	Unit Testing and Integration Testing will be done for R2.	Properties of product changes as required
8	CRUD for buyers(buyer account)	Buyer logged in	CRUD buyer account	Selected accounts must be modified as per requirements depending on permissions of user.	Unit Testing and Integration Testing will be done for R2.	Properties of buyer account changes as required
9	Direct CRUD Buyer Order	Buyer logged in	Adds buyer account.	User is registered as a buyer	Unit Testing and Integration Testing will be done for R2.	User gets registered as buyer
10	Buyer Login	Buyer not logged in	Logs in buyer via login portal	Buyer is logged in and can access ourfood site	Unit Testing and Integration Testing will be done for R2.	User logs in as buyer.

## Instructions
Test plan Instructions

It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
	Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
	Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests

Test No.	User Story covered	Preconditions	Test Description	Expected Outcome	R1 Outcome	R2 Outcome
1	Move Player	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester1		Player 1 is located at Reading Railroad cell.
2	Move Player	Test 1 completed	Player 1 Dice Roll Total : 5 / Player 1 End Turn	Player 1 is located on Jail cell.
3	Move Players in Turns	Game is in test mode. / Game is in initial state. / Number of Players: 2 / Player 1 Name: Tester1 / Player 2 Name: Tester2	Player 1 Dice Roll: 5 / Player 1 End Turn	Player 1 is located at Reading Railroad
			Player 2 Dice Roll: 3 / Player 2 End Turn	Player 2 is located at Baltic Avenue
4	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 39 / Player 1 End Turn	Player 1 is located at Boardwalk
			Verify Player 1 bank balance	Player 1 has $1500
5	Pass Go	Game is in test mode / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 40 / Player 1 End Turn	Player 1 is located on GO cell
			Verify Player 1 bank balance	Player 1 has $1700	Go money paid out only after passing GO, not when it is reached.
6	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 41 / Player 1 End Turn	Player 1 is located at / Mediterranean Avenue
			Verify Player 1 bank balance	Player 1 has $1700